## Sheet1
Risks Identified | Description | Likelyhood (5) | Impact (5) | Mitigration Strategy
Beacon Purchase Price | Purchasing the amount of beacons necessary is a large upfront cost and reimbursment might take a while | 5 | 1 | Have the group all contribute to purchasing the beacons to allow for an equal amount paid.
BLE Ranges too short | BLE nodes range may not cover the entire building with our current supply. | 2 | 2 | Check the range of the BLEs to cover the building chosen. If required, buy more BLEs.
Navigine integration is unsucessful | Inability to integrate navigine properly into Android. | 2 | 5 | Read documentation focused on integrating into Android and Android devices provided by Navigine.