## Sheet1
Risks Identified | Description | Likelyhood (5) | Impact (5) | Mitigration Strategy
Finding tools and software | Need to finds tools, such as APIs and SDKs, that will help in mapping task. | 5 | 4 | Researching into different available APIs and SDKs to help in task and choosing the right tools
Choosing development language(s) | Picking a development language that we don't know or will have to be learned to achieve required objectives | 3 | 3 | Looking into capabilities of languages known to avoid need for a new language. Self-training and tutorials if needed to be learned.
Running out of time | Not budgeting enough time to tasks and not being able to complete objectives on time. | 2 | 5 | Properly setting enough time and resources to tasks, as well as supporting the team with issues.
Cost | May have to buy beacons for the project, which will limit the amount of beacons available. | 3 | 5 | Find out if beacons can be provided.